## Instructions
Severity | Description
Low Impact (1 points) | Unimportant. Typo error or small user interface alignment issues.
High Impact (5 points) | The system runs. However, some non-critical functionalities are not working.
Critical Impact(10 points) | The system is down or is un-usable after a short period of time. We have to fix the bugs to continue.
Points in Iteration | Action
Points < 10 | Use the planned debugging time in the iteration.
Points >= 10 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.

## Bug Metrics
Bug Metrics
S/N | Iteration | Function | Description | Severity | Points | Final Bug Metric (Points Total) | Mitgation
1 | 1 | Bootstrap | Crashes on upload with an "undefined variable" | High | 5 | 66 | Stop current development and resolve the bug immediately. Project Manager reschedules the project.
2 | 1 | Bootstrap | Crashes on upload with $header returning a BOOLEAN instead of an array | High | 5
3 | 1 | Bootstrap | Does not return $results sorted alphabetically | Low | 1
4 | 1 | Login | Front-end Development (All in HTML) does not match with Back-End (PHP, JSON) | High | 5
5 | 1 | Login | Only allows login with '@' included due to input type = email | High | 5
6 | 1 | Login | Able to access admin page through student user authentication and vice versa | High | 5
7 | 1 | Login | Does not return expected testcase for json authentication | High | 5
8 | 1 | Login | Upon entering a successful/unsuccessful username/password in the website leads to a blank page | Critical | 10
9 | 1 | Login | Entering the website for the first time shows "invalid token" | Low | 1
10 | 1 | Bootstrap | Uploading the file on bootstrap.php shows a blank page | Critical | 10
11 | 1 | Bootstrap | When access to ‘bootstrap-process.php’ directly, it shows undefined index | High | 5
12 | 1 | Login | When access to 'login.php' directly, it shows error messages of 'Username should not be empty' and 'Password should not be empty' | High | 5
13 | 1 | Login | Able to access student timetable planner without logging in/admin authentication | Low | 1
14 | 1 | Login | Able to access check out bid page without logging in/admin authentication | Low | 1
15 | 1 | Login | Unable to logout from student timetable planner and check out bid page | Low | 1
16 | 1 | Login | Unable to access student home page from student timetable planner and check out bid page | Low | 1
17 | 2 | Protect | The page returns an infinite loop when studentIndex.php, Placebid.php & bidProcess.php is accessed without loggin in | Low | 1 | 22 | Use the planned debugging time in the iteration.
18 | 2 | Bidding | Displays an error "You have bidded for another section of this course" when updating the bid with an amount higher than the amount of e$ the student has | Low | 1
19 | 2 | Bidding | Updating a bid with a lower amount leads to the student losing more e$ | Low | 1
20 | 2 | Bidding | Updating a bid with the same name but different case leads to the student losing e$ | Low | 1
21 | 2 | Drop Section | User cannot drop a section when round 2 starts | High | 5
22 | 3 | Bootstrap | Bootstrap does not activate round 1 upon unsuccessful completion of it | Low | 1 | 4 | Use the planned debugging time in the iteration.
23 | 3 | Protect | Token is not acquired via POST/GET but SESSION variables | Low | 1
24 | 3 | TestCases | Testcases do not run as expected | Low | 1
25 | 3 | UI | Stop Start round doesn't show up as a modal | Low | 1
26 | 4 | Bidding | Bidding for a course with a decimal returns me a rounded number | Low | 1 | 8 | Use the planned debugging time in the iteration.
27 | 4 | Bidding | Bidding for a course does not take into account timetable clashes with enrolled courses | High | 5
28 | 4 | Clearing | Clearing a section with only 1 size returns an undefined offset error | Low | 1
29 | 4 | Bootstrap | Insertion of 0's returns me a blank 'header' | Low | 1
30 | 5 | TestCases | Invalid exam date due to input of string value | Low | 1 | 1 | Use the planned debugging time in the iteration.
31
32
33
34
35
36
37
38
39
40

## Bug Log
Bug Log
S/N | Iteration | Function | Description | Status | Discovered On | Resolved On | Fixed by (PP Team) | Results
1 | 1 | Bootstrap | Crashes on upload with an "undefined variable" | Resolved | 2019-09-16 | 2019-09-19 | G & M
2 | 1 | Bootstrap | Crashes on upload with $header returning a BOOLEAN instead of an array | Resolved | 2019-09-19 | 2019-09-23 | G & M
3 | 1 | Bootstrap | Does not return $results sorted alphabetically | Resolved | 2019-09-23 | 2019-09-26 | G & M
4 | 1 | Login | Front-end Development (All in HTML) does not match with Back-End (PHP, JSON) | Resolved | 2019-09-28 | 2019-09-29 | K & A
5 | 1 | Login | Only allows login with '@' included due to input type = email | Resolved | 2019-09-28 | 2019-09-29 | K & A
6 | 1 | Login | Able to access admin page through student user authentication and vice versa | Resolved | 2019-09-29 | 2019-09-29 | K & A
7 | 1 | Login | Does not return expected testcase for json authentication | Resolved | 2019-09-29 | 2019-09-29 | K & A
8 | 1 | Login | Upon entering a successful/unsuccessful username/password in the website leads to a blank page | Resolved | 2019-09-30 | 2019-09-30 | K & A
9 | 1 | Login | Entering the website for the first time shows "invalid token" | Resolved | 2019-09-30 | 2019-09-30 | K & A
10 | 1 | Bootstrap | Uploading the file on bootstrap.php shows a blank page | Resolved | 2019-09-30 | 2019-10-04 | G & A
11 | 1 | Bootstrap | When access to ‘bootstrap-process.php’ directly, it shows undefined index | Resolved | 2019-09-30 | 2019-09-30 | G & M
12 | 1 | Login | When access to 'login.php' directly, it shows error messages of 'Username should not be empty' and 'Password should not be empty' | Resolved | 2019-09-30 | 2019-10-03 | G & A
13 | 1 | Login | Able to access student timetable planner without logging in/admin authentication | Resolved | 2019-09-30 | 2019-09-30 | K & A
14 | 1 | Login | Able to access check out bid page without logging in/admin authentication | Resolved | 2019-09-30 | 2019-09-30 | K & A
15 | 1 | Login | Unable to logout from student timetable planner and check out bid page | Resolved | 2019-09-30 | 2019-09-30 | K & A
16 | 1 | Login | Unable to access student home page from student timetable planner and check out bid page | Resolved | 2019-09-30 | 2019-09-30 | K & A
17 | 2 | Protect | The page returns an infinite loop when studentIndex.php, Placebid.php & bidProcess.php is accessed without loggin in | Resolved | 2019-10-04 | 2019-10-05 | G & A
18 | 2 | Bidding | Displays an error "You have bidded for another section of this course" when updating the bid with an amount higher than the amount of e$ the student has | Resolved | 2019-10-04 | 2019-10-05 | G & A
19 | 2 | Bidding | Updating a bid with a lower amount leads to the student losing more e$ | Resolved | 2019-10-04 | 2019-10-05 | G & A
20 | 2 | Bidding | Updating a bid with the same name but different case leads to the student losing e$ | Resolved | 2019-10-04 | 2019-10-05 | G & A
21 | 2 | Drop Section | User cannot drop a section when round 2 starts | Resolved | 2019-10-14 | 2019-10-29 | G & S
22 | 3 | Bootstrap | Bootstrap does not activate round 1 upon unsuccessful completion of it | Resolved | 2019-10-24 | 2019-10-25 | G & S
23 | 3 | Protect | Token is not acquired via POST/GET but SESSION variables | Resolved | 2019-10-24 | 2019-10-25 | G & S
24 | 3 | TestCases | Testcases do not run as expected | Resolved | 2019-10-29 | 2019-10-29 | A & M
25 | 3 | UI | Stop Start round doesn't show up as a modal | Resolved | 2019-10-30 | 2019-10-30 | A & M
26 | 4 | Bidding | Bidding for a course with a decimal returns me a rounded number | Resolved | 2019-10-31 | 2019-11-01 | G & K
27 | 4 | Bidding | Bidding for a course does not take into account timetable clashes with enrolled courses | Resolved | 2019-10-31 | 2019-11-01 | G & K
28 | 4 | Clearing | Clearing a section with only 1 size returns an undefined offset error | Resolved | 2019-10-31 | 2019-11-01 | G & K
29 | 4 | Bootstrap | Insertion of 0's returns me a blank 'header' | Resolved | 2019-10-31 | 2019-11-01 | G & K
30 | 5 | TestCases | Invalid exam date due to input of string value | Resolved | 2019-11-12 | 2019-11-12 | G & K
31
32
33
34