## Week 11
Person | Question | Week: 29 October 2019 to 5 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Weekly Meeting | UAT | UAT Rectifications | Not a working day | Not a working day | Not a working day
| What will you do today? | Weekly Meeting | UAT | UAT Rectifications | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Weekly Meeting | UAT | UI Rectifications | Not a working day | Not a working day | UI Rectifications
| What will you work on today? | Weekly Meeting | UAT | UI Rectifications | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Drop Section should not display "no enrolment record found" | Weekly Meeting | UAT | Test Cases Rectifications | Not a working day | Not a working day | Test Cases
| What will you work on today? | Weekly Meeting | UAT | Test Cases Rectifications | Not a working day | Not a working day | Test Cases | Test Cases
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Cleaning up code for Round 2 Clearing Logic | Weekly Meeting | UAT | Test Cases Rectifications | Not a working day | Not a working day | Test Cases (JSON)
| What will you work on today? | Weekly Meeting | UAT | Test Cases Rectifications | Not a working day | Not a working day | Test Cases (JSON) | Test Cases (JSON)
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Update Bid Function | Weekly Meeting | UAT | Min Bid Rectifications | Not a working day | Not a working day | Not a working day
| What will you work on today? | Weekly Meeting | UAT | Min Bid Rectifications | Not a working day | Not a working day | Not a working day | Scheduling
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 10
Person | Question | Week: 22 October 2019 to 29 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Weekly Meeting | Consultation with prof | Test Cases | Not a working day | Fixed dump webservices to display a number with 1 d.p. for edollars | Fixed dump webservices to display a number with 1 d.p. for edollars
| What will you do today? | Weekly Meeting | Consultation with prof | Test Cases | Not a working day | Fixed dump webservices to display a number with 1 d.p. for edollars | Not a working day | Test Cases
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Weekly Meeting | Consultation with prof | Not a working day | Scheduling | Scheduling | Not a working day
| What will you work on today? | Weekly Meeting | Consultation with prof | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Not a working day | Weekly Meeting | Consultation with prof | Round 2 Clearing Logic | Not a working day | Not a working day | Drop Section should not display "no enrolment record found"
| What will you work on today? | Weekly Meeting | Consultation with prof | Round 2 Clearing Logic | Not a working day | Not a working day | Drop Section should not display "no enrolment record found" | Drop Section should not display "no enrolment record found"
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | TestCases (Admin Functions - JSON) | Weekly Meeting | Consultation with prof | Round 2 Clearing Logic | Not a working day | Round 2 Clearing Logic | Not a working day
| What will you work on today? | Weekly Meeting | Consultation with prof | Round 2 Clearing Logic | Not a working day | Round 2 Clearing Logic | Not a working day | Cleaning up code for Round 2 Clearing Logic
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Weekly Meeting | Consultation with prof | Test Cases | Not a working day | Not a working day | Not a working day
| What will you work on today? | Weekly Meeting | Consultation with prof | Test Cases | Not a working day | Not a working day | Not a working day | Update Bid Function
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 5
Person | Question | Week: 17 September 2019 to 24 September 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Worked on bootstrap feature, created classes and DAOs. | Creation of some validations for bootstrap | Not a working day | 2/3 completion of boostrap, logic validations for bid.csv incomplete. Bug still not squashed completely | Not a working day | Not a working day
| What will you do today? | Implement Boostrapping in BIOS. | Creation of some validations for bootstrap | Not a working day | Completion of Validations and bug checking | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | Not a working day | NIL | NIL | NIL | Validating H:MM and HH:MM and how to find whether a certain time is more than another | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Presentation slides for Week 7 | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Presentation slides for Week 7 | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day | Presentation slides
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Not a working day | Worked on bootstrap feature, created classes and DAOs. | Not a working day | Not a working day | Create methods for DAOs and cleanup | Not a working day | Not a working day
| What will you work on today? | Implement Boostrapping in BIOS. | Not a working day | Not a working day | Create methods for DAOs. | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Login Function (Preperation) | Not a working day | Not a working day | Json Validation (Login) | Not a working day | Testing Login Function, Fix Bugs, Push to Github
| What will you work on today? | Login Function (Preperation) | Not a working day | Not a working day | Json Validation (Login) | Not a working day | Testing Login Function, Fix Bugs, Push to Github | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Not a working day | Editing test cases for login page | Not a working day | Finalise test cases for login page | Not a working day | Tried running the test cases for login page
| What will you work on today? | Not a working day | Editing test cases for login page | Not a working day | Finalise test cases for login page | Not a working day | Tried running the test cases for login page | Tried resolving the error
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | Gave runtime error | NIL

## Week 6
Person | Question | Week: 24 September 2019 to 1 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric Clean up of bootstrap | Checking of bugs for bootstrap validation | Not a working day | Completion of bid validations for bootstrap and if time permits, sort the results it in alphabetical order | Not a working day | Do up json test cases for Bootstrap
| What will you do today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Checking of bugs for bootstrap validation | Not a working day | Completion of bid validations for bootstrap and if time permits, sort the results it in alphabetical order | Not a working day | Do up json test cases for Bootstrap | Not a working day
| Do you have any obstacles? | NIL | bid.csv logic validations are complicated | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Gantt Chart, Presentation Slides | Not a working day | Not a working day | Not a working day | Presentation Slides Integrate back-end to front-end
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Gantt Chart, Presentation Slides | Not a working day | Not a working day | Not a working day | Presentation Slides Integrate back-end to front-end | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | Not a working day | NIL
Mary Heng | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) Clean up of bootstrap | Checking of bugs for bootstrap validation | NIL | Completed bootstrap feature | NIL | Do up json test cases for Bootstrap
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Checking of bugs for bootstrap validations | Not a working day | Try to finish up bootstrap validations and start on bootstrap test cases | Not a working day | Do up json test cases for Bootstrap | Not a working day
| Do you have any obstacles? | NIL | Bid.csv logic validations are complicated | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Critical Path | Login (Testing) | Not a working day | Not a working day | Fixed Bugs and Commited Login Function to Github
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Critical Path | Login (Testing) | Not a working day | Not a working day | Fixed Bugs and Commited Login Function to Github | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Weekly Meeting (After Class) | Not a working day | Not a working day | Continued developing test cases for bidding for a section | Not a working day
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | Weekly Meeting (After Class) | Not a working day | Not a working day | Continued developing test cases for bidding for a section | Not a working day | Not a working day
| Do you have any obstacles? | Passing session id as token | NIL | NIL | NIL | NIL | NIL | NIL

## Week 7
Person | Question | Week: 1 October 2019 to 8 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Brushing up of code & bug fixes from iteration 1 | Bidding | Not a working day
| What will you do today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Brushing up of code & bug fixes from iteration 1 | Bidding | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review, Front-End (admin) integration - Display bootstap error on front-end | Not a working day | Brushing up of code & bug fixes from iteration 1 | Bidding | Front-end intergration for bidding page
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Brushing up of code & bug fixes from iteration 1 | Bidding | Front-end intergration for bidding page | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Not a working day | JSON (Admin Functions) | JSON Validation (Admin)
| What will you work on today? | Weekly Meeting (Scheduling, Critical Path, Bug Metric) | PM Review | Not a working day | Not a working day | JSON (Admin Functions) | JSON Validation (Admin) | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Delete/Update Bid, Drop Section | Weekly Meeting | Not a working day | Not a working day | JSON (Admin Functions) | Not a working day
| What will you work on today? | Delete/Update Bid, Drop Section | Weekly Meeting | Not a working day | Not a working day | JSON (Admin Functions) | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 8
Person | Question | Week: 8 October 2019 to 15 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting + Completion of drop bid & round 1 clearing logic | Completion of bidding results and json delete bid | Creation of drop bid and drop bid web service + completion of update bid web service | Not a working day | Not a working day
| What will you do today? | Not a working day | Weekly Meeting + Completion of drop bid & round 1 clearing logic | Completion of bidding results and json delete bid | Creation of drop bid and drop bid web service + completion of update bid web service | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | When to showcase the 'pending' in the bidding result | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Drop a section | Weekly Meeting | Dump Section | Integration front-end with back end - viewing of bidding results, dump user | Dump User, Dump Section, Dump Table, Dump Bid, Stop Round | Not a working day
| What will you work on today? | Drop a section | Weekly meeting | Weekly Meeting (Day 2) | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Weekly Meeting (Day 2) | Not a working day | Not a working day | Test Cases
| What will you work on today? | Not a working day | Weekly Meeting | Weekly Meeting (Day 2) | Not a working day | Not a working day | Test Cases | Test Cases
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Weekly Meeting (Day 2) | Completion of Dump Table | Not a working day | Not a working day
| What will you work on today? | Not a working day | Weekly Meeting | Weekly Meeting (Day 2) | Completion of Dump Table | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Weekly Meeting (Day 2) | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 9
Person | Question | Week: 15 October 2019 to 22 October 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day
| What will you do today? | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Test Cases | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | TestCases (Admin Functions - JSON)
| What will you work on today? | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | TestCases (Admin Functions - JSON) | TestCases (Admin Functions - JSON)
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | JSON Rectifications
| What will you work on today? | Weekly Meeting + Preparation for Application Demostration & Progress Update | App Demo and Progress Review | Not a working day | Not a working day | Not a working day | JSON Rectifications | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 12
Person | Question | Week: 5 November 2019 to 12 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Improved back-end integration with front-end for Round | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day
| What will you do today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Front End Refinements | Not a working day | Weekly Meeting | Front End for Bid Status | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Test Cases | Test Cases | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Test Cases | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Test Cases | Test Cases | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Test Cases | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Scheduling | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Not a working day
| What will you work on today? | Not a working day | Weekly Meeting | Not a working day | Test Plan | Not a working day | Not a working day | Not a working day
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 13
Person | Question | Week: 12 November 2019 to 19 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion
| What will you do today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion | Preparation for Final Sbumssion
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Agnes Lam | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion
| What will you work on today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion | Preparation for Final Sbumssion
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Mary Heng | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion
| What will you work on today? | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion | Preparation for Final Sbumssion
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Kwan Yang | What did you do yesterday? | Not a working day | Test Cases | Weekly Meeting | Not a working day | Not a working day | Schedule, Bug Metrics | Preparation for Final Sbumssion
| What will you work on today? | Test Cases | Weekly Meeting | Not a working day | Not a working day | Schedule, Bug Metrics | Preparation for Final Sbumssion | Preparation for Final Sbumssion
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL
Shourya Goenka | What did you do yesterday? | Not a working day | Not a working day | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion
| What will you work on today? | Test Plan | Weekly Meeting | Not a working day | Not a working day | Not a working day | Preparation for Final Sbumssion | Preparation for Final Sbumssion
| Do you have any obstacles? | NIL | NIL | NIL | NIL | NIL | NIL | NIL

## Week 14
Person | Question | Week: 12 November 2019 to 19 November 2019
|  | Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
Glen See | What did you do yesterday?
What will you do today?
Do you have any obstacles?
Agnes Lam | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Mary Heng | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Kwan Yang | What did you do yesterday?
What will you work on today?
Do you have any obstacles?
Shourya Goenka | What did you do yesterday?
What will you work on today?
Do you have any obstacles?